## Projects
Name | Objective | Department | Customer | Engagement Type | Billing Model | Priority | Start Date | End Date | Value | Currency | Primary PM | Secondary PM
Security Assessment | Perform vulnerability assessments and compliance audits. | Application Security | Acme Financial Services | FixedPrice | FixedPrice | High | 2026-07-01 | 2026-09-30 | 45000 | USD | John Smith | Smith John
Cloud Infrastructure Migration | Migrate legacy servers to AWS cloud environments. | Application Security | Acme Financial Services | ManagedServices | TimeAndMaterial | Medium | 2026-08-15 | 2027-02-15 | 120000 | USD | John Smith

## Security Assessment Phases
Name | Description | Order | Status | Start Date | End Date
Discovery & Planning | Kick-off, scoping and requirement gathering. | 1 | Active | 2026-07-01 | 2026-07-31
Assessment Execution | Run vulnerability scans and penetration tests. | 2 | Planned | 2026-08-01 | 2026-09-15
Reporting & Closure | Compile findings and present final report. | 3 | Planned | 2026-09-16 | 2026-09-30

## Security Assessment Tasks
Title | Description | Priority | Status | Assignee | Phase | Start Date | End Date | Effort Hours
Kick-off Meeting | Conduct initial project kick-off meeting with stakeholders. | High | To_Do |  | Discovery & Planning | 2026-07-01 | 2026-07-02 | 4
Scope Document | Define and document the engagement scope. | High | To_Do |  | Discovery & Planning | 2026-07-03 | 2026-07-10 | 16
Network Vulnerability Scan | Run automated scans across the internal network. | Critical | To_Do |  | Assessment Execution | 2026-08-01 | 2026-08-05 | 24

## Security Assessment Milestones
Title | Target Date | Weight (%) | Status | Phase
Scope Document Approved | 2026-07-10 | 20 | Pending | Discovery & Planning
Assessment Complete | 2026-09-15 | 50 | Pending | Assessment Execution
Final Report Delivered | 2026-09-30 | 30 | Pending | Reporting & Closure