## Projects
Name | Objective | Department | Customer | Engagement Type | Billing Model | Priority | Start Date | End Date | Value | Currency | Primary PM | Secondary PM | Status
UAT Reimport Sample | Sample workbook for DEF-P1-030 re-import without duplication. Import twice to verify update (not duplicate). | Application Security | Acme Financial Services | ManagedServices | TimeAndMaterial | Medium | 2026-07-06 | 2026-09-18 | 50000 | USD | John Smith |  | Draft

## UAT Reimport Sample Phases
Name | Description | Order | Status | Start Date | End Date
Phase 1 — Discovery | Kickoff and requirements | 1 | Planned | 2026-07-06 | 2026-07-17
Phase 2 — Design | Architecture and security review | 2 | Planned | 2026-07-20 | 2026-08-07
Phase 3 — Delivery | Build, UAT, sign-off | 3 | Planned | 2026-08-10 | 2026-09-18

## UAT Reimport Sample Tasks
Title | Description | Priority | Status | Assignee | Phase | Start Date | End Date | Effort Hours
Kickoff | Project kickoff | High | To_Do |  | Phase 1 — Discovery | 2026-07-06 | 2026-07-07 | 16
Requirements Workshop | Capture requirements | High | To_Do |  | Phase 1 — Discovery | 2026-07-08 | 2026-07-17 | 64
Architecture Design | Solution architecture | Medium | To_Do |  | Phase 2 — Design | 2026-07-20 | 2026-07-31 | 80
Security Review | Security design review | High | To_Do |  | Phase 2 — Design | 2026-08-03 | 2026-08-07 | 40
Implementation | Build and configure | Medium | To_Do |  | Phase 3 — Delivery | 2026-08-10 | 2026-09-04 | 160
UAT | User acceptance testing | High | To_Do |  | Phase 3 — Delivery | 2026-09-07 | 2026-09-15 | 56
Project Sign-OFF | Final sign-off | Critical | To_Do |  | Phase 3 — Delivery | 2026-09-18 | 2026-09-18 | 8

## UAT Reimport Sample Milestones
Title | Target Date | Weight (%) | Status | Phase
Discovery Complete | 2026-07-17 | 20 | Pending | Phase 1 — Discovery
Design Approved | 2026-08-07 | 30 | Pending | Phase 2 — Design
Go-Live / Sign-OFF | 2026-09-18 | 50 | Pending | Phase 3 — Delivery